## Bug Report
Bug Report | [10 empty] | Solved | 90 | Clear | 90 | TOTAL | #REF!
Project: Bench Education Web Application (Version: 1.1.10) | [10 empty] | In progress | 7 | Rework Needed | 15
Test Executed By: Mithun Nandi (66370) |  | Start Date: 15 Nov 2024 | End Date: Continues | [7 empty] | Intended part | 36
Module | Issue | Steps | in | Severity | Priority | Assigned Developer | Status | DEV Comment | Sanity Test Status | Remark | Total (Issues Count) | 142 | Total (Regression Tested) | 105
Login | Forgot password button is not clickable |  |  | low | Low | Rupok | Intended part |  | Done |  | No Action Taken | 9 | Total Pending | 31
| Validate that after 5-6 incorrect attempts, the system lock the account or provide a warning. |  |  | Medium | Low | Rupok | Intended part |  | Done
Dashboard | Most dashboard elements are static. |  | https://drive.google.com/file/d/1bRQ-zE97YWnBH2tV_ag84JNebxrQId06/view?usp=sharing | Medium | Medium | Rupok | Intended part | Backend API Issue | Done
| Returning to dashboard is so tough. Need to add a home button. |  |  | High | High | Rupok | Intended part |  | Done
General | Clicking from one module to another, then using the browser's back button to go back to the last module results in both modules being highlighted | Login > Module 1 > Module 2 > Click back button | https://drive.google.com/file/d/1mzaMpGB6jOLSkCBh6yfc_acyF_XJwx4Q/view?usp=sharing | low | Low | Rupok | Intended part |  | Done
| Cannot scroll past here, categories obfuscated in UI | Login > scroll | https://drive.google.com/file/d/1nOkjpDkXncFU0LotErehrLMx2IJriMi-/view?usp=sharing | low | Low
Academic | Edit a version name Only one character can be added or deleted each time | Login>Academic>Version>Edit | N/A | Medium | Medium | Rupok | Intended part | Revamp needed | Done
| No space between "versionname" in error message | Login>Academic>Version>Add new | https://drive.google.com/file/d/1yfMaLnWqE7vI7OLNE8FpGaCn2s5wfUJ2/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Try to create and edit version using inappropriate/long/unusual entries. | Login>Academic>Version>Edit> Enter numeric value | https://drive.google.com/file/d/1m404m8tKSZLd0S87y5Thlel5lS0Wz0IL/view?usp=sharing | Medium | Medium | Rupok | Intended part | Revamp needed | Done
| Group data did not found | Login>Academic>Group | https://drive.google.com/file/d/1ybvmt4K67MYSCmoKg4Kug7Tl8qX3H6TN/view?usp=sharing | low | Low | Rahi | Solved |  | Done
| Group Search not working | Login>Academic>Group | https://drive.google.com/file/d/1UOu-Vjbbs0_NwD5oUTlJOKCGvlcM-P1k/view?usp=sharing | Medium | Medium | Rupok | Intended part | search not needed here | Done
| Does not indicate error when clicking save | Login > Academic > Group > Add New > Incorrect values | https://drive.google.com/file/d/1Q1usX67Xn91YrDCCv_JVH-ee8CvwqAjT/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Only one character can be added or deleted each time | Login>Academic>Session | N/A | Medium | Medium | Rupok | Intended part | Revamp needed | Done
| Editing session name field saved with unallowed values | Login>Academic>Session | https://drive.google.com/file/d/17BZGOhHuJBxtl2-Y-hZPiVEEZkADvMhk/view?usp=sharing | low | Low | Rupok | Intended part | Revamp needed | Done
| Date should be in DD/MM/YYYY format | Login>Academic>Session | https://drive.google.com/file/d/18Nlx7msjJmvngOZ7qU2LRE75cnxEgHnG/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Date should be in DD/MM/YYYY format | Login>Academic>Session | https://drive.google.com/file/d/1EvmCsAVRHulCQ3DexHcb5e2oCEgNZ686/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Creating section with unallowed values | Login>Academic>Section>Add new | https://drive.google.com/file/d/1sWkbqImaoWaYELXZOWGuJStGmZSinrYE/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Class section should be before class subject | Login > academic |  | Medium | Medium
| Only one character can be added or deleted each time | Login>Academic>Section>Edit | N/A | low | Low | Rupok | Intended part | Revamp needed | Done
| Editing section name field saved with unallowed values | Login>Academic>Section>Edit> Enter numeric value | https://drive.google.com/file/d/1FxQFA40HxKcVG4nVkse3341Xinu8Ixlz/view?usp=sharing | low | Low | Rupok | Intended part | Revamp needed | Done
| In Edit subject one character can be added or deleted each time | Login>Academic>Subject>Edit | N/A | low | Low | Rupok | Intended part | Revamp needed | Done
| Editing subject name, code, type field saved with unallowed values | Log In>Academic>Subject>Edit> Enter numeric value | https://drive.google.com/file/d/1O9HiN261G6VB4-I4EfzJmOIhhwGtEFA0/view?usp=sharing | low | Low | Rupok | Intended part | Revamp needed | Done
| Can insert empty subject with space character | Login>Academic Subject>Add new > use spaces in Subject Name field | N/A | low | Low | Rupok | Solved |  | Done
| No confirmation notification when adding new Subject | Login>Academic>Subject>Add New | N/A | low | Low | Rupok | Solved |  | Done
| App crashes when clicking on Subject Type heading | Login>Academic>Subject>Subject Type | https://drive.google.com/file/d/1u-z-jCasTR_710qJt6aUdvWDuMdN3s98/view?usp=sharing | Medium | Medium | Rupok | Solved |  | Rework Needed | solved
| Spelling Error in Class Name Column | Login>Academic>Class | https://drive.google.com/file/d/1sG5JASHBG8wTt4B0COMzmM2HsvGrOSmU/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Can insert empty Class Name with space character | Login>Academic>Class>Add new > use spaces in Class Name field | N/A | low | Low | Rupok | Solved |  | Done
| Class code does not show in view | Login>Academic>Class | https://drive.google.com/file/d/1uWWgiZWXxKYdWQCm_avfIfnmCJmBTbA9/view?usp=sharing | Medium | Medium | Rupok | Solved | class code not need | Done
| Created class without classname, List view shows null | Login>Academic>Class>Add new | https://drive.google.com/file/d/1rBe3RGh3euqeglyMOahoKl4zpz-eu_Xj/view?usp=sharing | High | High | Rupok | Solved |  | Rework Needed | solved
| Created class without required field code | Login>Academic>Class>Add new | N/A | Medium | Medium | Rupok | Solved |  | Done
| Once selected edit, only one letter at a time can be edited | Login>Academic>Class | N/A | low | Low | Rupok | Intended part | Revamp needed | Done
| Proper validation needed while creating a class code, class code created with letter | Login>Academic>Class | N/A | Medium | Medium | Rupok | Solved |  | Done
| Mandatory field floor type can't be created from front end | Login>Academic>Class Room>Add new>Input field>Save | N/A | low | Low | Rupok | Solved
| Once selected edit, only one letter at a time can be edited | Login>Academic>Class Room>Edit | N/A | low | Low | Rupok | Intended part | Revamp needed
| Can insert empty Classroom and building name with space character | Login > Academic > Class room > add new | n/a | low | Low | Rupok | Solved
| invalid error message | Login>Academic>Class Room>Add new>Save | https://drive.google.com/file/d/1uVFdmZpvyWl9oQYqqND1dbIn3qlL-lmB/view?usp=sharing | low | Low | Rupok | Solved
| Class Period accepts Start Time that is after End time | Login>Academic>Class Period>Add New | https://drive.google.com/file/d/1WEHjiWezT6rjXGNQYtDZVtEghhopWZyx/view?usp=sharing | low | Medium
| Once selected edit, only one letter at a time can be edited | Login>Academic>Class Period>Edit | N/A | low | Low | Rupok | Intended part | Revamp needed | Done
| Class Period is not deletable | Login>Academic>Class Period | https://drive.google.com/file/d/1iYOE8xcIxclkxoEch25nv3ogJXfkTsjK/view?usp=sharing | low | Low | Rupok | Intended part | Delete permission should assign from admin panel | Done
| Cannot sort by time | Login>Academic>Class Period | https://drive.google.com/file/d/1XQ44DqgQtrcd_Ps2DZkLspXfoLrlmMbd/view?usp=sharing | low | Low | Rupok | Solved |  | Rework Needed
| Created class period without name | Login>Academic>Class Period>Add new | https://drive.google.com/file/d/1YbMRGl1-zZK6Gwthy6uFU70FziFAwmWl/view?usp=sharing | High | High | Rupok | Solved |  | Rework Needed | using space characters, still able to create empty class
| Once selected edit, only one letter at a time can be edited | Login>Academic>Class Subject>Edit | N/A | low | Low | Rupok | Intended part | Revamp needed | Done
| Created class subject without filling mandatory field group, version, class name | Login>Academic>Class Subject>Add new | https://drive.google.com/file/d/1A2pr2xyADriLdqoYHZ2DfhcGQQlzyKLw/view?usp=sharing | Medium | Medium | Rupok | Solved |  | Done
| If clicked without filling any fields all star marked fields doesn't show as required | Login>Academic>Class Subject>Add new>Input field>Save | https://drive.google.com/file/d/1kp57hie7kE_6Sw77ArVWBpH0p9z_8UGT/view?usp=sharing | low | Low | Rupok | Solved
| App crashes when clicking on Group heading | Login>Academic>Class Subject>Group | https://drive.google.com/file/d/1AtpdF2FMvFVYrz0E49y-rkS94XQtlVxq/view?usp=sharing | Medium | Medium | Rupok | Solved |  | Done
| Editing does not works | Login>Academic>Class Section>Edit |  | High | High | Rupok | Solved |  | Rework Needed | Trying to edit a value other than class section throws an error saying "Class Section already exists"
| Cannot sort by group | Login>Academic>Class Section>Edit | https://drive.google.com/file/d/1-6iPbBA-15Q8SL6ZL82yNOOUZCxSOk1a/view?usp=sharing | low | Low | Rupok | Solved |  | Rework Needed
| No Delete option | Login>Academic>Class Section>Delete |  | low | Low | Rupok | Intended part | Delete permission should assign from admin panel
| Created class subject without filling mandatory field group | Login>Academic>Class Section>Add new |  | low | Low | Rupok | Solved |  | Done
| App crashes when clicking on Group heading | Login>Academic>Class Section>Group | https://drive.google.com/file/d/1E4y4l0_0brWI0TpBuOs77yv1EJiBeZ3I/view?usp=sharing | Medium | Medium | Rupok | Solved |  | Done
| Once selected to add a new routine and then clicked on a date (ex: monday), the creating form and the add new button both disappears. even reloading the page does not fetch all functionality | Login>Academic>Class routine>Add new>Select weekly day name |  | High | High |  | Solved |  | Done
| Class routine does not show proper informations | Login>Academic>Class routine>search | https://drive.google.com/file/d/1PG5_ruwoRcKouWflpwWW1qhq1nkxYA_h/view?usp=sharing | High | High |  | Solved |  | Done
| Delete button does not works on Class Routine | Login>Academic>Class routine>add new>Delete a previously created class routine |  | Medium | Medium |  | Solved |  | Done
| Editing does not works | Login>Academic>Assign class teacher>Edit |  | High | High | Rupok | Solved |  | Done
| No Delete option | Login>Academic>Assign class teacher>Delete | https://drive.google.com/file/d/1yj5t_sQuBm0uvauQ_EzWF8qnAhRJkfCP/view?usp=sharing | low | Low | Rupok | Intended part | Delete permission should assign from admin panel | Done
| Created Assign class teacher without filling required field Group | Login>Academic>Assign class teacher>Add new>Input field>Save | https://drive.google.com/file/d/15E-yc6mhAAHtyIqG5DazQsvbeWiDGzgq/view?usp=sharing | low | Low | Rupok | Solved |  | Done
Student info | Spelling mistake Guardian details. On the last complete registration page, Finish button becomes Next once clicked and cancelled | Student info>Student admission> Guardian details>Guardian image |  | low | Low | Rahi
| Spelling mistakes in student info - Personal Info: First Name, Permanent Address Former Education: Institution Name and Institution Address Guardian Detail: First Name, Guardian Image, | Student Info > Student Admission | https://drive.google.com/file/d/1mcdU1_TzyMAEDQd2LePEs66ab_O0Lcl9/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| The final view function does not work if optional fields skipped, Guardian details does not show although filling all fields | Student info>Student admission> Complete personal details than skip both optional fields and final submission poage | https://drive.google.com/file/d/17C9HSqZ9N19gDzqt0FCFn2FOAvPvDMRr/view?usp=sharing | Medium | Medium | Rahi | Solved
| Guardian information missing in view menu. Editing student admission creates separate student details in list every time | Student info>Student admission> final details | https://drive.google.com/file/d/1eQ7o_pb-nAumhY2Vkol59yVewT70tdRg/view?usp=sharing | Medium | Medium | Rahi | Solved
| Created without filling Religion, Blood group, Birth Reg no | Student info>Student admission> Complete the form>Save | https://drive.google.com/file/d/1SYJo5DGb15Cq9qKW8jH69n9AlkU2Qkzu/view?usp=sharing | Medium | Medium | Rahi | Solved | this is the p.m requirement without filling those fields | Done
| Only three occupation options available | Student info>Student admission> Complete the form>Save | https://drive.google.com/file/d/11lDu_sbCo4YliLNr2EqiS2W-W-40fkKI/view?usp=sharing | Medium | Medium | Rahi | Intended part | it's create from admin panel setup because it just like a district list which is fixed | Done
| No mobile number validation on Guardian details | Student info>Student admission> Guardian details |  | low | Low | Rahi | Solved |  | Done
| Birth reg certificate does not specify file type. Could not add a file in birth reg certificate. Although Image added, no marker appear to confirm that. | Student info>Student admission form |  | Medium | Medium | Rahi | Solved | On the frontend, I implement display error messages and preview uploaded images and files. The backend currently allows file types other than images and PDFs, which is need to be stopped
| Shift assigned but does not show in attendance tab | Student info>Student Details>View>Attendance | https://drive.google.com/file/d/1Z9pDsKevc9U--WWYPBgH8v5pQGRBbuKA/view?usp=sharing | low | Low | Rahi | Solved |  | Done
| In editing mode some field in admission details disappears. Can't edit admission details | Student info>Student Details>edit>admission details | https://drive.google.com/file/d/14MIM-UeVByIwVHEuhi8zhuWPwWjpIoPO/view?usp=sharing | Medium | Medium | Rahi
| Delete button does not works | Student info>Student Details>Delete a student details |  | Medium | Medium | Rahi | Solved |  | Done
| Fees collected but not shown in student details . The fees clear indicator (X) sign is still there. | Student info>Student Details |  | Medium | Medium
Human Resource | Unable to edit Department | Login>Human resource>Department>Edit |  | Medium | Medium | Rupok | Solved |  | Rework Needed | Can only edit 1 character at a time
| Unable to edit Designation | Login>Human resource>Designation>Edit |  | Medium | Medium | Rupok | Solved |  | Rework Needed | Can only edit 1 character at a time
| Updater id does not appear | Login>Human resource>Shift | https://drive.google.com/file/d/1XMHknG7l9VkmzQv-jDPMceah705oAxgu/view?usp=sharing | low | Low | Rupok | Solved
| Division Name does not start with capital letter | Login>Human Resource>Division>Add New | https://drive.google.com/file/d/1pgjYFzdCwNpFdYS1OHBei81tDyxCJJvl/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Sorting by division name not working properly | Login>Human Resource>Division> Click division header | https://drive.google.com/file/d/1w6GKLOiFNlQn6VwfI_Gi2CIIYm5qVCHZ/view?usp=sharing | low | Medium | Rupok | Solved |  | Done
| Sorting by district name not working properly | Login>Human Resource>District> Click district header | https://drive.google.com/file/d/1k83BjJ_VztGndwvG-4WjEnGsqxnYs5wx/view?usp=sharing | low | Medium | Rupok | Solved |  | Done
| Sorting by country name does not work properly, and stops sorting after first click | Login>Human Resource>Country>Click country header | https://drive.google.com/file/d/1FNJN_n6A3uLCD4OC-Tc8HPjOzhucAoA_/view?usp=sharing | low | Medium | Rupok | Solved |  | Done
| Sorting by thana name not working properly | Login>Human Resource>thana> Click thana header | https://drive.google.com/file/d/1cyHl_nMYfLfFZUJDhVldBw-UNVEMFc5f/view?usp=sharing | low | Medium | Rupok | Solved |  | Done
| Sorting by board name not working properly | Login>Human Resource>board> Click board header | https://drive.google.com/file/d/1raIDrnOABhBH1SU2Bfw_NFcagcvc3Vlp/view?usp=sharing | low | Medium | Rupok | Solved |  | Done
| Date should be in DD/MM/YYYY format | Login > Human Resource > Board | https://drive.google.com/file/d/19hKUEdzXnmLwW6iYSShaTz4-X-rrd66N/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Date should be in DD/MM/YYYY format | Login>Human Resource>Staff Directory | https://drive.google.com/file/d/1X4VZQvcIRUvlRsdQtQQV5Q8Rim-h79mg/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| While selected editing from final check, Bank info shows multiple data. If selected staff education and payroll from editing, Save & Continue button does not work. No error message shown. | Login>Human Resource>Staff Directory>Add new>Complete or check>edit | https://drive.google.com/file/d/1N6bLbunsxd7Iz0kcAhxy2jQvHqSGdYkM/view?usp=sharing | High | High | Rupok | Solved |  | Done
| Payroll, Social media information, and occasionally staff education does not show on the final page. Need proper validation. | Login>Human Resource>Staff Directory>Add new>Complete or check | https://drive.google.com/file/d/14DmJZGuUXLbuSwm37-7UEmye18crKMlO/view?usp=sharing | Medium | Medium | Rupok | Solved |  | Rework Needed
| Clicking the go to list button after finish creating a staff directory takes to student details page | Login>Human Resource>Staff Directory>Add new>Go to list |  | Medium | Medium | Rupok | Solved |  | Done
| On payroll Salary fields such as gross, basic, medical, convence accepted entry with letters only | Login>Human Resource>Staff Directory>payroll>Add using inappropiate values |  | low | Low | Rupok | Solved |  | Done
| After clicking view button profile does not show all information as created for validation issue | Login>Human Resource>Staff Directory>View Button>Profile | 30.png | High | High | Rupok | Solved |  | Done
| Payroll tab not working | Login>Human Resource>Staff Directory>View Button>Payroll |  |  |  | Rupok | Solved |  | Rework Needed | Payroll field is blank when clicked
| Staff Directory Bug after adding information | Login > Human Resource > Staff Directory | https://drive.google.com/file/d/1HYuW2qGPSr1zUB3whkQQLcqUCZXY3j2O/view?usp=sharing | Medium | Medium
| Duplicate staff created when trying to edit | Login>Human Resource>Staff Directory>Action>Edit | https://drive.google.com/file/d/1-54DkTkYtdeBZBFzRHkm9lCXsX3ZfUZN/view?usp=sharing | Medium | Medium | Rupok | Solved |  | Done
| Spelling Error | Login>Human Resource>Staff Directory>Add New>Personal Information>Permanent Address | https://drive.google.com/file/d/1tdkMUIhhjT9HnwVc371MyJKFdDwbM-d3/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| While creating Staff attendance final save button does not respond | Login>Human Resource>Staff Attendance>Add new>Input field>Save |  | High | High | Sudipto | Solved |  | Done
| While creating staff attendance, AFTER clicking save after searching while NOT having typed in a remark, the remark field only accepts 1 character at a time | Login>Human Resource>Staff Attendance>Add new>Input field>Save>Type in Remark | https://drive.google.com/file/d/1Y7tOjii8nto1EiLFsWwVqx4lBlECQ0Ce/view?usp=sharing | Medium | Medium |  | Intended part |  | Done
| Date should be in DD/MM/YYYY format | Login>Human Resource>Staff Attendance>Add new | https://drive.google.com/file/d/1RPlxjAiYJ5Ka5RN9m0kQcSFYUe8yUcyS/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Sort by leave type name not working | Login > Human Resource > Leave Type > click on leave type name header | https://drive.google.com/file/d/1Ceo5sFNrTyf2G1yw8Ge3E8hPzke1z7Ew/view?usp=sharing | low | Medium | Rupok | Solved |  | Done
| No space between "LeaveType" | Login>Human Resource>Leave Type | https://drive.google.com/file/d/1_DlWvZVTWmZFwNJcFvlynGWxmE76rqgI/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Remark option's required mark should be removed as it is not a required field | Login>Human Resource>Leave Type>Add new | https://drive.google.com/file/d/1ZS8IWa_Zka7sgXXScNOm0eZza8u9lqq2/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Applying leave does not work | Login>Human Resource>Apply Leave>Add new | https://drive.google.com/file/d/1wWycRQWFnGIj9ffB7EPWVLjU1Y-rl5FZ/view?usp=sharing | High | High | Rahi | Solved |  | Done
| Staff Leaves Search option does not work | Login>Human Resource>Staff Leave>Search | https://drive.google.com/file/d/1vXyAr-WbF8ATi1ui5J_y9SceA1VIrTtY/view?usp=sharing | Medium | Medium | Rahi | Solved |  | Rework Needed
| Required mark should be removed from End date | Login>Human Resource>Stuff status>Add new | https://drive.google.com/file/d/19zDQqGxpinVhXR9oAa_z--_6m0QRWRir/view?usp=sharing | low | Low | Rahi | Solved |  | Done
| Edit button does not work | Login>Human Resource>Stuff status>Edit | https://drive.google.com/file/d/10TByeIJc1WD6UxBrIb_NslRHi69Mzuws/view?usp=sharing | Medium | Medium | Rahi | Solved |  | Done | Edit button missing
| Delete button does not work | Login>Human Resource>Stuff status>Delete | https://drive.google.com/file/d/10TByeIJc1WD6UxBrIb_NslRHi69Mzuws/view?usp=sharing | low | Low | Rahi | Solved |  | Done | Delete button missing
|  | Login>Human Resource>Holiday>Delete | https://drive.google.com/file/d/1mXadynnjH8ClG7fv8KdvnZ_oe0LBoj_p/view?usp=sharing | low | Low | Rupok | Intended part |  | Done
| In Holiday, under the Week/Day tabs after clicking the arrows to select next, the event flashes for a brief moment before disappearing. After this, the events also disappear from the Month tab | Login>Human Resource> Holiday> Week/Day>Click to next week/day of event | https://drive.google.com/file/d/1I6NQfAyZHWKad2kl16wpDNiwCJ10orwv/view?usp=sharing | High | High | Rupok | Intended part |  | Done
| Holiday accepts invalid values like "!" and allows start time to be after end time | Login>Human Resource> Holiday> Add Event | https://drive.google.com/file/d/1E-wWnmV8ljTU21TqblEcWC7Rg7fsHD9Q/view?usp=sharing | low | Low | Rupok | Solved |  | Rework Needed | end date can still be set to before start date
| Date should be in DD/MM/YYYY format | Login>Human Resource> Holiday> Add Event | https://drive.google.com/file/d/19kC4Lsh62gObyct08uRG956_Afsfm_h9/view?usp=sharing | low | Low | Rupok | Intended part |  | Done
| Salary Setup accepts minimum value greater than maximum value | Login>Human Resource>salary setup > add salary setup | https://drive.google.com/file/d/1C20B57pv6n6foUiKAJRCqum8jbrjUsiR/view?usp=sharing | Medium | Medium | Rahi | In progress
Exam | App crashes when sorting by Start Mark or End Mark | Login > Exam > Grade > Start Mark/End Mark | https://drive.google.com/file/d/1kqbrpTtJZM-4W0AMaKR16h_eg6KiURxT/view?usp=sharing | Medium | Medium | Rupok | Solved |  | Done
| Serial no. not showing when clicking edit | Login > Exam > Grade > Edit |  |  |  | Rupok | Solved
| Start mark and end mark should not require decimals | Login > Exam > Grade >Add new | https://drive.google.com/file/d/1WYjD4S44ENcv7H76aOGUdpJVaPYNonrC/view?usp=sharing | low | Low | Rupok | Intended part
| Inserting new grade adds it to the end of the table instead of beginning | Login > Exam > Grade > Add New | https://drive.google.com/file/d/1HbFysPtVJTnAe5FZV1LuTk40eIiAfetn/view?usp=sharing | low | Low | Rupok | Intended part
| Grammar Error in notificaiton when adding new exam | Login > Exam > Exam Name> Add New | https://drive.google.com/file/d/15HBf84FoF9sHMM6lSghMv0ddoxo7PXTf/view?usp=sharing | low | Low | Rupok | Solved
| Purpose of active toggle unclear | Login > Exam > Exam Name > Add New | https://drive.google.com/file/d/1BlkWOu1AJCjrrRlqeHXvn17TjRDqwkPs/view?usp=sharing | low | Low | Rupok | Solved | Current exam should be active | Done
| Inserting new exam adds it to the end of the table instead of beginning | Login > Exam > Exam Name> Add New | https://drive.google.com/file/d/1lbsp4xsrlyBnL6quAG7aZNaLWu6WezJz/view?usp=sharing | low | Low | Rupok | Intended part | Use serial no
| Does not indicate error when clicking save trying to create a new exam that already exists | Login > Exam Name > Add new (with same name as existing exam) > save | n/a | low | Low | Rupok | Solved |  | Rework Needed | Throws generic error message instead of stating what the error is (exam already exists)
| If the exam name is same, serial number and active inactive troggle can't be edited | Login>Exam>Exam name>Edit |  | low | Medium | Rupok | Solved |  | Done
| App crashes when selecting exam routine view | Login>Exam>Exam Routine View | https://drive.google.com/file/d/1LCs2c9JzWA61eNDzdXlkB8x36XPDuOzN/view?usp=sharing | High | High | Rupok | Intended part | Have to login with valid ID | Done
| Spelling Errors | Login>Exam>Exam Routine>Add New | https://drive.google.com/file/d/134-AtGu2853xBpUpxkPYR0rJpCLsvPnu/view?usp=sharing | low | Low | Rupok | Solved |  | Rework Needed | Solved
| Inserting new exam routine adds it to the end of the table instead of beginning | Login>Exam>Exam Routine>Add New | N/A | low | Low | Rupok | Intended part
| When creating exam routine, "Edit" button is a required field to complete new addition. Edit Icon should not be displayed, instead something much more visible should be placed to indicate it is mandatory | Login > exam > exam routine > add new > edit | https://drive.google.com/file/d/1phKsU75UmbcIup7dFnC_1DSBFIXQHXRz/view?usp=sharing | High | High | Rupok | Solved
| Selecting Session on Admit Card crashes the application | Login>Exam>Admit Card>Select version than session | https://drive.google.com/file/d/1TZ0Rs41pf-gaf41m4n0BMt-J_hHzHljr/view?usp=sharing | High | High | Rupok | Solved |  | Done
| Admit card does not include version, class name, session, section or routine | Login > Exam > admit card > search | https://drive.google.com/file/d/1kElX1gM9Wi1L_3ogzvrZdeVyhWz-Ewp8/view?usp=sharing | High | High | Rupok | Intended part | Exam should be valid | Done
| Group option should not exist for classes under 9 | Login > Exam > admit card | n/a | Medium | Medium | Rupok | Intended part |  | Done
| cannot un-select group option after selecting | Login > exam > admit card > group | n/a | Medium | Medium | Rupok | Solved
| Group name in admit card says "n/a" even when group is selected | Login > Exam > admit card > search | https://drive.google.com/file/d/1t_2AKSMVfr1nxfeAXGDtMM9qZ5mfFSRl/view?usp=sharing | Medium | Medium | Rupok | Intended part |  | Done
Fees Collection | Search function in all of Fees Collection group does not work | Login>Fees Collection>Fees type/discount/entry | https://drive.google.com/file/d/18mu9LrCRA1oTPBq1OCNkGHjFEVbMU4dH/view?usp=sharing | low | Low | Rupok | Intended part |  | Done
| Sorting in Fees Collection Group not working | Login>Fees Collection>Fees type/discount/entry | https://drive.google.com/file/d/1yVW14RZE6UUV6WQlAssgKoSyaGSq2Uaz/view?usp=sharing | low | Low | Rupok | Solved |  | Rework Needed | Fees discount and fees entry sorting still not functional
| "Select Category" is a selectable option in category of fees type | Login>Fees Collection>Fees type> Add new | https://drive.google.com/file/d/19O5RvAqQUiT9ni2VD42LHaYOmuJiqhh0/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| When adding new fees discount entry, having an unlabeled toggle button for switching between amount and percentage can lead to confusion | Login>Fees Collection>Fees dicount>Add New | https://drive.google.com/file/d/1VFMl5PWTFabQ3hIuLSbV_72m5J9BSQSD/view?usp=sharing | low | Low | Rupok | In progress
| Clicking on Actions in fees collection group crashes the app | Login>Fees Collection>Fees type/discount/entry>Actions | https://drive.google.com/file/d/1YkZuRQnyPHFfDc_4nvGWo-RhXtQtElfh/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Created Fees Discount without required field s Amount, Remark, Description | Login>Fees Collection>Fees Discount>Create | https://drive.google.com/file/d/1x9dgTmU3JjfneQTCjEx0FIjfX3umXaaD/view?usp=sharing | Medium | Medium | Rupok | In progress
| The amount field should only take input of numbers | Login>Fees Collection>Fees Discount>Create |  | low | Low | Rupok | In progress
| The troggle should indicate that inputed amount is flat or in percentage | Login>Fees Collection>Fees Discount>Create | https://drive.google.com/file/d/182MISLf5nmzNztOmi_5i2BbHKmWJ8-H-/view?usp=sharing | low | Low | Rupok | In progress
| After successfully created a Fees Entry the pop up message does not appear normally | Login>Fees Collection>Fees entry>Add new |  | low | Low |  | Solved
| Error found while Selecting Session on Collect Fees | Login>Fees Collection>Collect fees>Add new | https://drive.google.com/file/d/1TZ0Rs41pf-gaf41m4n0BMt-J_hHzHljr/view?usp=sharing | High | High | Rupok |  | Pls Provide proper SS
| Collect Fees does not seem to work | Login>Fees Collection>Collect fees>Add new | https://drive.google.com/file/d/1D7JIWwv8oBOt9Ch9XgGkEw1A8IE-ULcG/view?usp=sharing | High | High | Rahi | In progress | Manually need to run schedular for new fees detail add
Communicate | Selecting Session on Send SMS crashes the application | Login>Communicate>Send SMS>Class>Session | https://drive.google.com/file/d/1i_vqNjN5PxRFW2sg0czepivTtYk2WcTG/view?usp=sharing | High | High |  | Solved |  | Done
| Ui elements exceed background | Login>communicate>Send SMS/Email | https://drive.google.com/file/d/1RCKRRM-BSCFop5KTjh4k7j7uUP0rNCq2/view?usp=sharing | low | Low
| Search function in Communicate group does not work | Login>Communicate>SMS/Email template | https://drive.google.com/file/d/1Wui03zSb8x4FvhCsRcKV2bJLND1-VB7p/view?usp=sharing | Medium | Medium
| Spelling Error (Failure) | Login > Communicate > email/sms log | https://drive.google.com/file/d/1HJSEBjAf-tGGW21_n_-OW8O5xRhagUpw/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Date should be in DD/MM/YYYY format | Login > Communicate > email/sms log | https://drive.google.com/file/d/1F0zt6Je11ahDG_ndsy8rHI_t6y6UNPss/view?usp=sharing | low | Low | Rupok | Intended part |  | Done
| App crash when sorting by message body | Login > communicate > email template > message body | https://drive.google.com/file/d/101oHsT5KYuaZpoNXdvXpyhMERM5gsYii/view?usp=sharing | Medium | Medium | Rupok | Solved |  | Done
| Selecting Session on Send Email crashes the application | Login>Communicate>Send Email>Class>Session |  | High | High |  | Solved |  | Done
| Shedule time can't be changed by editing for emails | Login>Communicate>Shedule Email/SMS log |  | low | Low
| Created notice without title. Should properly define required fields | Login>Communicate>Notice board>Add new | https://drive.google.com/file/d/1SribDH6qxs9kp58-tO8nETBJ4kSI2cRs/view?usp=sharing | Medium | Medium | Rahi | In progress
Reports | On Employee information if searched for an employee 2nd time after changing department, shows multiple employee's data | Login>Reports>Employee Information>Search one than change department and search again | https://drive.google.com/file/d/1J_g2F6mr3tvT-btXWe79jG32bdJRPHfg/view?usp=sharing | Medium | High | Sudipto | Solved
| Employee information not working | Login>Reports>Employee information>Search one than change department and search again | https://drive.google.com/file/d/1qVGJeL5oiJ7rn7OQscb_tD2JhKbUstCV/view?usp=sharing | High | High | Sudipto | Solved
Tasks
Accounts
Process
Purchase
Inventory

## Role Student
User Role: Student | [10 empty] | Solved | 7 | Clear | 6
Executed By: Mithun Nandi(66370) | [10 empty] | In progress | 0 | Rework Needed | 1
Version: 1.1.10 | [6 empty] | Start Date: |  | End Date: |  | Intended part | 0
Module | Issue | Steps | Screenshot | Severity | Priority | Assigned Developer | Status | DEV Comment | Sanity Test Status | Remark | Total (Issues Count) | 7 | Total (Regression Tested) | 7
Student Info | A student should not be able to edit and delete other student's info. | Login>Student Info>Student details>Edit, Delete |  | High | High | Rupok | Solved |  | Done |  | No Action Taken | 0 | Total Pending | 1
| Clicking edit button on a student details does responds page is restricted. | Login>Student Info>Student details>Edit/Update |  | low | Low | Rupok | Solved | student details not need | Done
| Error found while selecting Profile. | Login>Student Info>Profile | https://drive.google.com/file/d/1TZ0Rs41pf-gaf41m4n0BMt-J_hHzHljr/view?usp=sharing | High | High | Rahi | Solved |  | Done
| Applying leave does not work (Save button not responding) | Login>Student Info>Apply Leave |  | High | High | Rupok | Solved | working fine. no issues | Done | Save button still does not respond
| Date should be in DD/MM/YYYY format | Login>Student Info>Apply Leave | https://drive.google.com/file/d/1UKfy1jCN4gEu8Viqvuv2s55i0D6MzuEW/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Responsible teacher shows undefined | Login>Student Info>Apply Leave | https://drive.google.com/file/d/1SkWpr5zk4rhmW3ptvXQPJNzQkXL0e1UO/view?usp=sharing | low | Low | Rupok | Solved | Not Bug. assign class teacher mandatory | Done
| Delete Leave not working | Login>student info>apply leave>delete |  | Medium | High | Rahi | Solved |  | Rework Needed | Says permission denied when deleting. If student cannot delete leave, then delete button should not be displayed
5

## Role Guardian
User Role Guardian | [10 empty] | Solved | 3 | Clear | 3
[11 empty] | In progress | 4 | Rework Needed | 0
[11 empty] | Intended part | 0
Module | Issue | Steps | Screenshot | Severity | Priority | Assigned Developer | Status | DEV Comment | Sanity Test Status | Remark | Total (Issues Count) | 7 | Total (Regression Tested) | 3
Dashboard | Guardian name + other information missing | login > dashboard | https://drive.google.com/file/d/1wsBbVc4Sbb7hitm8kOJrHgiXUAerTL67/view?usp=sharing | Medium | Medium | Rupok | In progress |  |  |  | No Action Taken | 0 | Total Pending | 4
Academic | Creating routing for guardian's child (from admin page) makes guardian crash whenever logging in | (admin login) > academic > class routine > create new routine for students class > login as guardian | n/a | High | High | Rupok | In progress
| Guardian should not have access to teacher's timetable | login (guardian) > academic > teaher's timetable | n/a | Medium | Medium | Rupok | Solved |  | Done
Student Info | Student details missing information | login > student info > student details | https://drive.google.com/file/d/1glV3CvO3rF11fkNjK9aSLPTat8y2LxlI/view?usp=sharing | Medium | Medium | Rupok | Solved | not need | Done
| Create leave not saving | login > student info > apply leave > apply leave | n/a | High | High | Rupok | In progress
Human Resource | Guardian should not have access to staff leaves | Login > human resource > staff directory | https://drive.google.com/file/d/16EAPBia4_QofZ3d_4RhUWlRIzQ6y-D-0/view?usp=sharing | Medium | Medium | Rupok | Solved |  | Done
Exam | Exam Routine View is blank | Login > Exam > Exam routine view | n/a | High | High | Rupok | In progress

## Role Teacher
User Role Teacher | [10 empty] | Solved | 24 | Clear | 22
[11 empty] | In progress | 1 | Re-work Needed | 3
[11 empty] | Intended part | 1
Module | Issue | Steps | Screenshot | Severity | Priority | Assigned Developer | Status | DEV Comment | Sanity Test Status | Remark | Total (Issues Count) | 26 | Total (Regression Tested) | 25
Academic | Clicking class routine shows application error | Teacher login>Academic>Class routine | https://drive.google.com/file/d/1TZ0Rs41pf-gaf41m4n0BMt-J_hHzHljr/view?usp=sharing | High | High |  | Solved |  | Done |  | No Action Taken | 0 | Total Pending | 4
| Class Name does not show on Teacher's timetable | Teacher login>Academic>Teacher's time table | https://drive.google.com/file/d/1m17RNhz2ZSdYRSbXYs-USzdMncOkqjzW/view?usp=sharing | low | Medium | Rupok, Muzhirul Islam | Solved | done | Rework Needed
| When logged in as teacher, Version is not selectable in class routine | Login(teacher)>Academic>Class Routine>version | https://drive.google.com/file/d/1ndSIxutYJK5Z61ZPmiAbxqFtFzWeM1FU/view?usp=sharing | High | High | Rupok | Solved |  | Done
Student Info | While adding Student Status, if end date is not selected, The start date becomes end date by defult | Teacher login>Student info>Student Status | https://drive.google.com/file/d/1DhczIIJXrO8i_Yrcl5wFosTmwbEUcyWU/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| The required mark should be removed from end date | Teacher login>Student info>Student Status>Add new | https://drive.google.com/file/d/1_G-TyVh_qjXB1b_HMENpK8Dv2bXZvros/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Says staff status added instead of student when adding new student status | Teacher login>Student info>Student Status>Add new | https://drive.google.com/file/d/1aaUMmvJXhE93ruHWtQCAstV9-9ye3Ooy/view?usp=sharing | low | Low | Rupok | Solved | done | Rework Needed | Still says staff status
| Does not indicate End Date is required | Teacher login>Student info>Sutdent Status>Add new | https://drive.google.com/file/d/1kUDT4ei8Jiw0nAr-Shjim91j0AqdwRr8/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Edit and Delete do not work | Teacher login>Student info>Sutdent Status>Edit/Delete | https://drive.google.com/file/d/1fSj9q4FRTc4EIB4bovMDO3gC0Ss6hl5M/view?usp=sharing | Medium | High | Rupok | Solved | Edit &Delete not needed. Removed now | Done
| Could not create attendance entry. Selecting session on attendance entry crashes the application | Teacher login>Student info>Attendance Entry | https://drive.google.com/file/d/1TZ0Rs41pf-gaf41m4n0BMt-J_hHzHljr/view?usp=sharing | High | High | Rupok | Solved |  | Done
| Selecting student leave application crashes the application | Teacher login>Student info>Student leave application | https://drive.google.com/file/d/1mFFtUWVW5ID-7GS-_LO7nIVgJSDkEMU0/view?usp=sharing | High | High |  | Solved |  | Done
Human Resource | Clear button does not works on staff attendance | Teacher login>Human Resource>Staff Attendance |  | low | Low |  | Solved |  | Done
| In teacher's Leave apply employee name shows undefined | Teacher login>Human Resource>Leave apply>Create leave | https://drive.google.com/file/d/19UwbP3GlVk0uw9PJsNgYkRrQUp4H_5mL/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| No required mark on required fields | Teacher login>Human Resource>Leave apply>Create leave | https://drive.google.com/file/d/1eTrLtZO5tApJnUqrllQf_DjVyPYZSR97/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Could not create leave, Leave type not found | Teacher login>Human Resource>Leave apply>Create leave | https://drive.google.com/file/d/1mv_GKhRPRlY6BRYidC7EDss1zjb0P4E7/view?usp=sharing | High | High | Rupok | Intended Part | Leave assign from backend | Done
| Date should be in DD/MM/YYYY format | Teacher login>Human Resource>Leave apply | https://drive.google.com/file/d/1k92F2-OxLs6ooDHpIdwit8mVDUbEZw-D/view?usp=sharing | low | Low | Rupok | Solved | done | Rework Needed | WHen clicking apply leave button, date format is still in mm/dd/yy
| Does not indicate whether leave application was successful when clicking save | Login(Teacher)>Human Resource>Apply Leave>Create>Save | https://drive.google.com/file/d/1QavQmE1ynQiIz7ROPV5_0_4beDVea2QN/view?usp=sharing | low | Medium |  | Solved |  | Done
| Search Leave does not work | Teacher Login>Human Resouce>Apply Leave>Search | https://drive.google.com/file/d/1_DVnjjj6LuqkhTJe-THWzMrGSyrmhayJ/view?usp=sharing | Medium | Medium | Rahi | Solved |  | Done
| Spelling Error (Applied) | Teacher login>Human Resource>Apply Leave>Create Leave | https://drive.google.com/file/d/1p6dUWY0YwPq6Y53YWCUW9d_0HqKjWqbB/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Can bypass mandatory address and reason field when applying for leave by using space characters | Teacher login>Human Resource>Apply Leave>Create Leave | https://drive.google.com/file/d/1uM2WsjFRL-gVQ_lY1zZg-8yjbPVHyXyC/view?usp=sharing | Medium | Medium | Rupok | Solved |  | Done
| Reset button is not functional in leave application form | Teacher login>Human Resource>Leave apply>Create leave |  | low | Low | Rahi | Solved |  | Done
| Cannot approve/deny leave, clicking view crashes app | Teacher login (responsible employee) > human resource > staff leaves > view | https://drive.google.com/file/d/1Y8_P1pZitldOJ4GNGSinpdhfON8T9Pav/view?usp=sharing | High | High | Rahi, Muzhirul Islam | Solved | muzhirul vai and rahi fixed this issue | Done
| Search function in staff leaves not working | teacher login > human resource > staff leaves > Search | N/A | Medium | Medium | Rahi, Muzhirul Islam | In progress | working on it |  | Search still does not filter results
Task | Could not create Task, No subject detected | Teacher login>Task>Teacher Task | https://drive.google.com/file/d/1ZnOJj6V2a-icO-l0EWJDC5xEBtfSBV0v/view?usp=sharing | High | High | Rupok , Sudipto | Solved |  | Done
| App crashes when trying to add new task | Login>Tasks>teacher Task>Create Task>Class Subject | https://drive.google.com/file/d/1DGz6yXEqL6PSd8tsH6ePosVEuv0lMUuS/view?usp=sharing | High | High | Rupok, Sudipto | Solved |  | Done
| Create task button can be more visible/ easy to nevigate | Teacher login>Task>Teacher Task | https://drive.google.com/file/d/1KQ0djhipZ_CLM_FMMkCaAQiSU9V2cBxo/view?usp=sharing | low | Low | Rupok | Solved |  | Done
| Spelling error (Assign) | Teacher login>Task>Teacher Task | https://drive.google.com/file/d/1ZU4g4youw1iFkue9oDzRyk94DyYv4zKD/view?usp=sharing | low | Low | Rupok | Solved |  | Done

## New version
New Version(1.2.10) Update Modules | [11 empty] | Solved | 15 | Clear | 15
Executed By: Mithun Nandi (66370) | [11 empty] | In progress | 2 | Rework Needed | 0
Version: 1.2.10 |  |  |  |  | Start Date: |  | End Date: |  |  |  |  | Intended part | 0
Module | Feature | Issue | Steps | Screenshot | Severity | Priority | Assigned Developer | Status | DEV Comment | Sanity Test Status | Remark | Total (Issues Count) | 20 | Total (Regression Tested) | 15
Purchase | Goods Receive | The item input boxes/box level are not aligned properly on a 14.0” display. | Login>Purchase>Good Receive>New Good Receive | https://drive.google.com/file/d/1vav9dD9VwwfdFYL3erOtYV-30bbG2yol/view?usp=sharing | low | Low | Rahi | Solved |  | Done |  | No Action Taken | 3 | Total Pending | 5
|  | Required fields are not marked properly, If saved without a required field, the navigational required field (red) marker does not appear. | Login>Purchase>Good Receive>New Good Receive | https://drive.google.com/file/d/1-3BXvGd9WY0k3ljHS8jAhReS6ys1MEbu/view?usp=sharing | low | Medium | Rahi | Solved |  | Done
|  | Some fields should only take input of specific type of data(Ex: Rcv Rate allows input of character) | Login>Purchase>Good Receive>New Good Receive | https://drive.google.com/file/d/1MF8rsungT9d97ec7F0p_mssWoW3xnNMj/view?usp=drive_link | low | Low | Rahi | Solved |  | Done
|  | Wrong Placeholder | Login>Purchase>Good Receive>New Good Receive | https://drive.google.com/file/d/1_hWJTgeevFuRz6smJqbajifQMqq38L8X/view?usp=sharing | low | Medium | Rahi | Solved |  | Done
|  | Confirmed with pay and confirmed without pay are not traceable in list view. | Login>Purchase>Good Receive | https://drive.google.com/file/d/1eNcQDq6xxrHzqWhJG5IX28tAlRGTeHwj/view?usp=drive_link | Medium | Medium | Rahi | Solved |  | Done
|  | Search bar does not work. | Login>Purchase>Good Receive |  | Medium | High | Rahi, Rupok | Solved |  | Done
|  | Confirm without pay did not show any PDF file. | Login>Purchase>Good Receive>New Good Receive |  | High | High | Rahi | Solved |  | Done
|  | Placeholder appearing like the 1st option in dropdown | Login>Purchase>Good Receive>New Good Receive | https://drive.google.com/file/d/1pGZV2HMPWriniRU3EaZx2AlkeVL-jLbY/view?usp=sharing | low | Low | Rahi | Solved |  | Done
| Supplier | Required fields should be specified. | Login>Purchase>Supplier>New Supplier | https://drive.google.com/file/d/1TRiluUQLf0VlhIO1DakjBm_1eA4hqW_I/view?usp=sharing | Medium | Medium | Rahi | Solved |  | Done
|  | Wrong error message | Login>Purchase>Supplier>New Supplier | https://drive.google.com/file/d/14tYL11PN2XtPpprllmOum0WqjwfZ3G95/view?usp=sharing | low | Low | Sudipto | Solved |  | Done
|  | The search box is currently non-functional and does not return any results. | Login>Purchase>Supplier | https://drive.google.com/file/d/14QfqrOI67PLk4LYrR2e7G1eZiE0owwEP/view?usp=drive_link | Medium | High | Rahi | In progress
| Supplier Payments | Required fields should be specified. | Login>Purchase>Supplier Payments>New Supplier Payment | https://drive.google.com/file/d/1ssV2M8vF8TlELB7IKaOiATq5vq4oIjnW/view?usp=sharing | low | Medium | Rahi | Solved |  | Done
|  | When creating Supplier Payments, the date is recorded correctly, but the created time always shows as 12:00 AM on list page. | Login>Purchase>Supplier Payments>New Supplier Payment | https://drive.google.com/file/d/1uacGtQVk7Tqk0Ge9S9_8NKIARnKO9PZI/view?usp=sharing | low | Medium | Rahi | Solved |  | Done
|  | Wrong Placeholder | Login>Purchase>Supplier Payments>New Supplier Payment | https://drive.google.com/file/d/1mgDvqClXaDGcrpZtRNx5z86XRLv7xKo6/view?usp=sharing | low | Medium | Rahi | Solved |  | Done
|  | After confirming once, the confirm and Save button still appears on details. | Login>Purchase>Supplier Payments>Select a supplier payment |  | low | Low | Rahi | Solved |  | Done
|  | The search box is currently non-functional and does not return any results. | Login>Purchase>Supplier Payments | https://drive.google.com/file/d/1zIWPDU5G4z6zuZyP2jq3bDa3f6_4OYLf/view?usp=drive_link | Medium | High | Rahi | In progress
Inventory | Model | If created with a similar name, The error message is not clear | Login>Inventory>Model |  | low | Low | Sudipto | Solved |  | Done
Dashboard | Admin | Payment Due field purpose is not clear. (The title should address the unit if it is taka amount or person count) | Login>Dashboard |  | low | Low
|  | Dashboard data unclear | Login>Dashboard | https://drive.google.com/file/d/1EyazkFGI5v7f6btVami-BXpiS4KIEF_4/view?usp=sharing | low | Low
|  | Stuff attendance data intrigration problem on dashboard | Login>Dashboard |  | low | Low